## Burn Sheet
Project | Custom Partner Solutions / OPP / FOIA FCSF
Budget | 50000
Average hourly rate (used for estimates): | GS-14 | 40 | per hour
Project participants |  |  | 2017-10-29 |  | 2017-11-05 |  | Copy and paste the previous two columns here and adjust the date to add more weeks to the project. | If you need to add columns past this point, be sure to change the formula for "Total Projected Hours" as needed.
|  |  | Est | Actual | Est | Actual
george.washington |  |  | 32 | 28 | 32 | 0
john.adams |  |  | 32 | 26 | 32 | 0
susan.b.anthony |  |  | 32 | 29 | 32 | 0
alexander.hamilton |  |  | 32 | 32 | 32 | 0
eleanor.roosevelt |  |  | 32 | 32 | 32 | 0
To add more project participants, copy the latest participant's row, insert a row beneath it, paste into the new row, and adjust the participant name as needed.
Total hours |  |  | 160 | 177 | 160 | 0
Budget remaining |  | 50000 | 43600 | 43220 | 36820 | 43220
Total projected hours | 320
Total hours used to date | 177
Total spent to date | 6780
Sanity checks
Other project participants | abraham.lincoln
If the above row is not empty, it means that people who are not listed as project participants have billed time for this project.
Other project weeks
If the above row is not empty, it means that there are weeks in which people have billed time for this project that are not reflected in the table above.

## Settings
Settings
Tock API key: | abcd123
This is a string of letters and numbers that gives this spreadsheet access to Tock.
Project prefix filter: | Custom Partner Solutions
This is optional. Set it to automatically filter out any timecard entries whose project name doesn't start with the value you provide.
Hourly rates
name | grade | rate
GS-11 | 11 | 10
GS-12 | 12 | 20
GS-13 | 13 | 30
GS-14 | 14 | 40
GS-15 | 15 | 50
SES | 16 | 60
Additional documentation
For additional documentation on this spreadsheet, see: |  | https://github.com/18F/tock-gas-ts

## Timecards
start_date | user | project_name | hours_spent | grade | amount_billed
2017-10-29 | george.washington | Custom Partner Solutions / OPP / FOIA FCSF | 28 | 14 | 1120
2017-10-29 | john.adams | Custom Partner Solutions / OPP / FOIA FCSF | 26 | 15 | 1300
2017-10-29 | susan.b.anthony | Custom Partner Solutions / OPP / FOIA FCSF | 29 | 12 | 580
2017-10-29 | alexander.hamilton | Custom Partner Solutions / OPP / FOIA FCSF | 32 | 15 | 1600
2017-10-29 | abraham.lincoln | Custom Partner Solutions / OPP / FOIA FCSF | 30 | 13 | 900
2017-10-29 | eleanor.roosevelt | Custom Partner Solutions / OPP / FOIA FCSF | 32 | 14 | 1280
2017-10-29 | thomas.jefferson | Custom Partner Solutions / USDA / Forest Service Design Consulting | 12 | 13 | 360
2017-10-29 | jane.adams | Custom Partner Solutions / USDA / Forest Service Design Consulting | 1 | 12 | 20
2017-10-29 | james.monroe | Custom Partner Solutions / USDA / Forest Service Design Consulting | 11.5 | 13 | 345