## Burn Sheet
Project | Custom Partner Solutions / OPP / FOIA FCSF
Budget | 100000
Average hourly rate (used for estimates): | GS-15 | 50 | per hour
Project participants |  |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8
|  |  | 2017-10-29 |  | 2017-11-05 |  | 2017-11-12 |  | 2017-11-19 |  | 2017-11-26 |  | 2017-12-03 |  | 2017-12-10 |  | 2017-12-17
|  |  | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual | Est | Actual
george.washington |  |  | 32 | 28 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | Copy and paste the previous two columns here to add more weeks to the project.
john.adams |  |  | 32 | 26 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
susan.b.anthony |  |  | 32 | 29 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
alexander.hamilton |  |  | 32 | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
eleanor.roosevelt |  |  | 32 | 32 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
person.6 |  |  | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
person.7 |  |  | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
person.8 |  |  | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0 | 32 | 0
To add more project participants, copy the latest participant's row, insert a row beneath it, paste into the new row, and adjust the participant name as needed.
Total hours |  |  | 256 | 177 | 256 | 0 | 256 | 0 | 256 | 0 | 256 | 0 | 256 | 0 | 256 | 0 | 256 | 0
Total amount billed |  |  | 12800 | 6300 | 12800 | 0 | 12800 | 0 | 12800 | 0 | 12800 | 0 | 12800 | 0 | 12800 | 0 | 12800 | 0
Budget remaining |  | 100000 | 87200 | 93700 | 80900 |  | 68100 |  | 55300 |  | 42500 |  | 29700 |  | 16900 |  | 4100
Total projected hours | 2048
Total hours used to date | 177
Total spent to date | 6300
Current budget remaining | 93700
Estimated final budget remaining | 4100
Sanity checks
Other project participants | abraham.lincoln
If the above row is not empty, it means that people who are not listed as project participants have billed time for this project.
Other project weeks
If the above row is not empty, it means that there are weeks in which people have billed time for this project that are not reflected in the table above.

## Settings
Settings
Tock API key: | abcd123
This is a string of letters and numbers that gives this spreadsheet access to Tock.
Project prefix filter: | Custom Partner Solutions
This is optional. Set it to automatically filter out any timecard entries whose project name doesn't start with the value you provide.
Hourly rates
name | grade | rate
UNKNOWN / BLANK | -1 | 35
GS-11 | 11 | 10
GS-12 | 12 | 20
GS-13 | 13 | 30
GS-14 | 14 | 40
GS-15 | 15 | 50
SES | 16 | 60
Note that the "UNKNOWN / BLANK" grade is used in certain cases where Tock doesn't have any grade information available. In this case, it might be useful to set the rate to some average value so that the budget calculations remain relatively accurate.
Additional documentation
For additional documentation on this spreadsheet, see: |  | https://github.com/18F/tock-gas-ts

## Timecards
start_date | user | project_name | hours_spent | grade | amount_billed
2017-10-29 | george.washington | Custom Partner Solutions / OPP / FOIA FCSF | 28 | 14 | 1120
2017-10-29 | john.adams | Custom Partner Solutions / OPP / FOIA FCSF | 26 | 15 | 1300
2017-10-29 | susan.b.anthony | Custom Partner Solutions / OPP / FOIA FCSF | 29 | 12 | 580
2017-10-29 | alexander.hamilton | Custom Partner Solutions / OPP / FOIA FCSF | 32 |  | 1120
2017-10-29 | abraham.lincoln | Custom Partner Solutions / OPP / FOIA FCSF | 30 | 13 | 900
2017-10-29 | eleanor.roosevelt | Custom Partner Solutions / OPP / FOIA FCSF | 32 | 14 | 1280
2017-10-29 | thomas.jefferson | Custom Partner Solutions / USDA / Forest Service Design Consulting | 12 | 13 | 360
2017-10-29 | jane.adams | Custom Partner Solutions / USDA / Forest Service Design Consulting | 1 | 12 | 20
2017-10-29 | james.monroe | Custom Partner Solutions / USDA / Forest Service Design Consulting | 11.5 | 13 | 345